## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5
Task Two | 2016-07-27 | 2016-08-01 | 5
Task Three | 2016-07-27 | 2016-08-04 | 8
Task Four | 2016-07-27 | 2016-08-06 | 10
Task Five | 2016-08-01 | 2016-08-09 | 8
Task Six | 2016-08-01 | 2016-08-05 | 4
Task Seven | 2016-08-03 | 2016-08-10 | 7
Task Eight | 2016-08-05 | 2016-08-12 | 7
Task Nine | 2016-08-06 | 2016-08-09 | 3
Task Ten | 2016-08-06 | 2016-08-10 | 4
Task Eleven | 2016-08-07 | 2016-08-13 | 6
Task Twelve | 2016-08-10 | 2016-08-16 | 6
Task Thirteen | 2016-08-14 | 2016-08-19 | 5
Task Fourteen | 2016-08-15 | 2016-08-23 | 8
Task Fifteen | 2016-08-16 | 2016-08-26 | 10
Task Sixteen | 2016-08-17 | 2016-08-28 | 11
Task Seventeen | 2016-08-18 | 2016-08-29 | 11
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43146 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Design and modelling | 2018-02-15 | 2018-02-19 | 4 | 3.2 | 0.8 | 80%
sketch of the mobile robot | 2018-02-15 | 2018-02-16 | 1 | 0.9 | 0.1 | 90%
sketch of robot manipulator | 2018-02-16 | 2018-02-17 | 1 | 0.9 | 0.1 | 90%
3D modelling of sketches with solidworks | 2018-02-17 | 2018-02-18 | 1 | 0.9 | 0.1 | 90%
Review of design and circuitry | 2018-02-18 | 2018-02-20 | 2 | 2 | 0 | 100%
Make adjustment if need | 2018-02-18 | 2018-02-20 | 2 | 2 | 0 | 100%
Building of 1st prototype | 2018-02-20 | 2018-02-26 | 6 | 4.2 | 1.8 | 70%
Preparing 2d files to laser cut-Morning | 2018-02-20 | 2018-02-21 | 1 | 1 | 0 | 100%
Cut component at the workshop and Assembly-afternoon | 2018-02-20 | 2018-02-21 | 1 | 0.8 | 0.2 | 80%
Complete Assembly | 2018-02-21 | 2018-02-22 | 1 | 0 | 1 | 0%
Review and adjustment of assembly | 2018-02-22 | 2018-02-26 | 4 | 0 | 4 | 0%
Programming of robot | 2018-02-27 | 2018-03-10 | 11 | 5.5 | 5.5 | 50%
Setup odroid with ubuntu and Ros | 2018-02-27 | 2018-02-28 | 1 | 0.8 | 0.2 | 80%
low level programming of robot | 2018-02-28 | 2018-03-01 | 1 | 0 | 1 | 0%
installation and impletation of navigation stack and other packages | 2018-03-01 | 2018-03-03 | 2 | 2 | 0 | 100%
configurating comunication between nodes(pieces of code)& further adjustment | 2018-03-03 | 2018-03-10 | 7 | 0 | 7 | 0%
Programming User friendly application for the robot | 2018-03-12 | 2018-03-25 | 13 | 1.3 | 11.7 | 10%
Preparation of prensentation of progress | 2018-03-12 | 2018-03-13 | 1 | 0 | 1 | 0%
Testing | 2018-02-27 | 2018-04-05 | 37 | 0 | 37 | 0%
Review of project & and adjustment if needed | 2018-03-27 | 2018-04-05 | 9 | 0 | 9 | 0%
Video ,pictures and or writing log of progress | 2018-02-15 | 2018-03-26 | 39 | 11.7 | 27.3 | 30%
Preparation of prensentation | 2018-04-05 | 2018-04-07 | 2 | 0.2 | 1.8 | 10%
literature review | 2018-04-07 | 2018-04-14 | 7 | 0 | 7 | 0%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43306 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Design and modelling | 2018-02-15 | 2018-02-20 | 5 | 2.5 | 2.5 | 50%
design of the layers of the robot | 2018-07-25 | 2018-07-30 | 5 | 2.5 | 2.5 | 50%
buiding the robot manipulator | 2018-07-27 | 2018-08-01 | 5 | 0 | 5 | 0%
Design the robot manipulator and produce URDF file(for visualization in rviz | 2018-07-27 | 2018-08-04 | 8 | 0 | 8 | 0%
Buiding the robot manipulator | 2018-07-28 | 2018-08-05 | 8 | 8 | 0 | 100%
Programming the mobile robot with general features | 2018-07-29 | 2018-08-06 | 8 | 6 | 2 | 75%
Programming the robot manipulator with general features | 2018-07-30 | 2018-08-03 | 4 | 1.4 | 2.6 | 35%
Building app | 2018-07-31 | 2018-08-07 | 7 | 1.75 | 5.25 | 25%
Literature review | 2018-08-01 | 2018-08-08 | 7 | 4.9 | 2.1 | 70%
Website online | 2018-08-02 | 2018-08-08 | 6 | 0.9 | 5.1 | 15%
Log progres with video and log book | 2018-08-03 | 2018-08-07 | 4 | 2.4 | 1.6 | 60%
Presentation | 2018-08-04 | 2018-08-10 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2018-08-05 | 2018-08-11 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2018-08-06 | 2018-08-11 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2018-08-07 | 2018-08-15 | 8 | 4 | 4 | 50%
Task Fifteen | 2018-08-08 | 2018-08-18 | 10 | 4 | 6 | 40%
Task Sixteen | 2018-08-09 | 2018-08-20 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2018-08-10 | 2018-08-21 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.